## Dashboard
Agile Management Dashboard — 10 Weeks
| Total Tasks |  | Completed |  | In Progress | Blocked
| 41 |  | 6 |  | 0 | 0
| Overall Completion | 14.63% |  | Open Risks | 20 | High Risks | 0
Member | Assigned Tasks | Completed Tasks | Completion %
Annemarie | 11 | 3 | 27.27%
Cobrin | 10 | 1 | 10%
Nick | 10 | 1 | 10%
Brandon | 10 | 1 | 10%
Week | Planned Pts | Completed Pts | Completion % | Sprint Status
1 | 0 | 0 | 0% | Not Started
2 | 0 | 0 | 0% | Not Started
3 | 0 | 0 | 0% | Not Started
4 | 0 | 0 | 0% | Not Started
5 | 0 | 0 | 0% | Not Started
6 | 0 | 0 | 0% | Not Started
7 | 0 | 0 | 0% | Not Started
8 | 0 | 0 | 0% | Not Started
9 | 0 | 0 | 0% | Not Started
10 | 0 | 0 | 0% | Not Started
Status | Count
Not Started | 35
In Progress | 0
Blocked | 0
Done | 6

## Agile Plan
10-Week Agile Management Plan
Week | Task / Story | Type | Owner | Priority | Status | Start Date | Due Date | Estimate (Pts) | Actual (Pts) | % Complete | Notes
1 | Create the agile plan | Task | Annemarie | High | Done | 2026-09-18 | 2026-09-25 | 4 |  | 100
1 | Make the flow chart for the back-end | Task | Annemarie | High | Done | 2026-09-18 | 2026-09-25 | 5 |  | 100
1 | Functional and non- Functional requirements, requirement priority, slides | Task | Cobrin | High | Done |  |  |  |  | 100
1 | Risk analysis, ethical issues, and frontend slides | Task | Nick | High | Done |  |  |  |  | 100
1 | Requirement slides | Task | Brandon | High | Done |  |  |  |  | 100
2 | Start to make the frame of the website | Task | Annemarie | Medium | Done | 2026-10-02 | 2026-10-03 | 6 |  | 100
2 | Look into the database set up | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
2 | Start drawing out what we want the UI to look like | Task | Nick | Medium | Not Started |  |  |  |  | 0
2 | Help with the background knowledge about weather and database | Task | Brandon | Medium | Not Started |  |  |  |  | 0
3 | Finish up the frame of the website | Task | Annemarie | High | Not Started |  |  |  |  | 0
3 | Finish up putting in the database | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
3 | Finish up with UI design | Task | Nick | Medium | Not Started |  |  |  |  | 0
3 | Finish with dataset | Task | Brandon | Medium | Not Started |  |  |  |  | 0
4 | Wrap up anything that wasn't finished and start back-end | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
4 | Start doing the back-end stuff | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
4 | Start putting the UI design into the program | Task | Nick | Medium | Not Started |  |  |  |  | 0
4 | Start doing back-end stuff | Task | Brandon | Medium | Not Started |  |  |  |  | 0
5 | Help finish up applying the UI | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
5 | Finish back-end stuff | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
5 | Finish applying the UI | Task | Nick | Medium | Not Started |  |  |  |  | 0
5 | Finish back-end stuff | Task | Brandon | Medium | Not Started |  |  |  |  | 0
6 | Start testing the website | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
6 | Start testing the website | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
6 | Start testing the website | Task | Nick | Medium | Not Started |  |  |  |  | 0
6 | Start testing the website | Task | Brandon | Medium | Not Started |  |  |  |  | 0
7 | Continue testing and debugging | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
7 | Continue testing and debugging | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
7 | Continue testing and debugging | Task | Nick | Medium | Not Started |  |  |  |  | 0
7 | Continue testing and debugging | Task | Brandon | Medium | Not Started |  |  |  |  | 0
8 | Finish testing and fixing the problems and turn in assignment | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
8 | Finish testing and fixing the problems and turn in assignment | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
8 | Finish testing and fixing the problems and turn in assignment | Task | Nick | Medium | Not Started |  |  |  |  | 0
8 | Finish testing and fixing the problems and turn in assignment | Task | Brandon | Medium | Not Started |  |  |  |  | 0
9 | Start putting all of our written things together | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
9 | Compile writing | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
9 | Compile writing | Task | Nick | Medium | Not Started |  |  |  |  | 0
9 | Compile writing | Task | Brandon | Medium | Not Started |  |  |  |  | 0
10 | Review written report and turn it in | Task | Annemarie | Medium | Not Started |  |  |  |  | 0
10 | Review written report | Task | Cobrin | Medium | Not Started |  |  |  |  | 0
10 | Review written report | Task | Nick | Medium | Not Started |  |  |  |  | 0
10 | Revire written report | Task | Brandon | Medium | Not Started |  |  |  |  | 0

## Sprint Tracker
Sprint Tracker — 10 Weeks
Week | Sprint Goal | Annemarie Pts | Cobrin Pts | Nick Pts | Brandon Pts | Planned Pts | Completed Pts | Completion % | Sprint Status | Sprint Notes
1 | Get the presentation demo done | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
2 | Confirm the database we are doing and the information we are comparing. Also start doing the frame of the website | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
3 | Finish doing the frame, add database and start making decisions on what it will look like | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
4 | Start applying the UI that we decided on and finish the back-end | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
5 | Finish applying the UI | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
6 | Start the testing phase | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
7 | Continue testing phase and fix problems along the way | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
8 | Finish testing and complete the deployment demo | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
9 | Start putting together the written report | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started
10 | Turn in the written report (by 11/30) | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## Risks & Issues
Risks & Issues Log
ID | Date Logged | Risk / Issue | Impact | Severity | Owner | Mitigation / Action | Due Date | Status | Resolution / Notes
R-01 |  |  |  | Medium |  |  |  | Open
R-02 |  |  |  | Medium |  |  |  | Open
R-03 |  |  |  | Medium |  |  |  | Open
R-04 |  |  |  | Medium |  |  |  | Open
R-05 |  |  |  | Medium |  |  |  | Open
R-06 |  |  |  | Medium |  |  |  | Open
R-07 |  |  |  | Medium |  |  |  | Open
R-08 |  |  |  | Medium |  |  |  | Open
R-09 |  |  |  | Medium |  |  |  | Open
R-10 |  |  |  | Medium |  |  |  | Open
R-11 |  |  |  | Medium |  |  |  | Open
R-12 |  |  |  | Medium |  |  |  | Open
R-13 |  |  |  | Medium |  |  |  | Open
R-14 |  |  |  | Medium |  |  |  | Open
R-15 |  |  |  | Medium |  |  |  | Open
R-16 |  |  |  | Medium |  |  |  | Open
R-17 |  |  |  | Medium |  |  |  | Open
R-18 |  |  |  | Medium |  |  |  | Open
R-19 |  |  |  | Medium |  |  |  | Open
R-20 |  |  |  | Medium |  |  |  | Open

## Retrospectives
10-Week Retrospectives
Week | What Went Well? | What Didn't Go Well? | What Should We Try? | Action Owner | Action Due | Follow-up Status
1 | [5 empty] | Not Started
2 | [5 empty] | Not Started
3 | [5 empty] | Not Started
4 | [5 empty] | Not Started
5 | [5 empty] | Not Started
6 | [5 empty] | Not Started
7 | [5 empty] | Not Started
8 | [5 empty] | Not Started
9 | [5 empty] | Not Started
10 | [5 empty] | Not Started

## Lists
Lists & Dropdown Values
Members | Status | Priority | Type | Risk Status | Severity
Annemarie | Not Started | High | Task | Open | High
Cobrin | In Progress | Medium | Story | Monitoring | Medium
Nick | Blocked | Low | Bug | Mitigated | Low
Brandon | Done |  | Milestone | Closed